## Estimates
Estimates
Features |  | Estimation (Days) |  | Phase
Area | Functionality | # Screens | Calculated | Phase
Project | Requirement Analysis & Documentation |  | 35 | 1
| System Architecture (Server & DB) |  | 14 | 1
Consumer Cross Platform Application | Splash Screen | 1 | 2 | 1
| Sign in / Sign up Screen | 1 | 3 | 1
| Sign in Screen | 1 | 3 | 1
| Sign up Screen | 6 | 9 | 1
| Connect Facebook Screen, G+, Twitter, LinkedIn | 1 | 3 | 1
| Facebook Permission Screen | 1 | 2 | 1
| Forgot Password Screen | 1 | 3 | 1
| Home Screen (with 2 buttons) + Bid Updates | 1 | 5 | 1
| Airline / Flight Search Screen | 1 | 4 | 1
| Airline / Flight Auction item Screen | 1 | 4 | 1
| Seat Map Screen | 1 | 11 | 1
| Bid Screen (Automatic OR Manual) | 2 | 6 | 1
| Bidding Engine + Push Notification |  | 21 | 1
Messages send out automatically to facebook | Winner Screen | 1 | 4 | 1
| Payment Screen | 1 | 11 | 1
- Multi CC cards should be stored for confirming payment - Send email with the confirmation number | Payment Confirmation & Thanks Screen | 1 | 3 | 1
| Payment Engine | 1 | 11 | 1
| Seat Selection Screen | 1 | 11 | 1
| Boarding Pass Screen | 1 | 11 | 1
| Loser Screen | 1 | 4 | 1
| Promotion Screen | 2 | 14 | 1
| Settings Screen | 2 | 3 | 1
Flight Manager Android Application | Splash Screen | 1 | 2 | 1
| Sign in Screen | 1 | 3 | 1
Create Auction
| - Airport / Flight Number Search Screen | 1 | 4 | 1
| - Flight information & confirmation Screen | 1 | 3 | 1
| - Seat Map Availability Screen | 1 | 11 | 1 | http://www.amadeus.com/airlineit/solutions/sol_2stand_1ecommerce_1eretail.html
| - Create / Edit / Confirm Auction items (by selecting seats) | 3 | 14 | 1
| - Starting Bid Amount Screen | 1 | 6 | 1
| - Auction Start / End Time | 1 | 3 | 1
| Auctions list (with edit/delete option) | 1 | 5 | 1
| Settings |  | 3 | 1
SeatBay Admin Control Panel (Web based) | Login Screen | 1 | 2
| Forgot Password | 1 | 2
| Remember me |  | 1
| Admin User Group Management | 3 | 4
| Admin User Management | 3 | 4
| Airline Management | 3 | 4
| Airline User Management | 3 | 7
| Ads Management |  | 10
| Promotions |  | 11
| Reports |  | 11
| Logout |  | 1
Web-services |  |  | 24
Analytics | SDI recommends http://www.flurry.com/index.html OR http://www.google.com/analytics/mobile/ |  | 1
QA (Crash report) | SDI recommends https://www.bugsense.com/ & http://appium.io/ |  | 2
Demo | Create demo for display on PC or Tablet-Consumer & Flight Admin interface screens |  | 20

## Assumptions
Assumption
Client wants the app in multiple language. Please provide us the list of languages to evaluate the additional time required
Client will provide Facebook account id for connect with facebook feature
Can a user place more than 1 bid at one time through the app?
Client will have to subscribe payment gateway & provide us the credentails before the start of the development
Client will have to subscribe for vault to store cc details eg: https://developer.paypal.com/webapps/developer/docs/api/#vault
Client will provide detailed specs how the payment will be transfered to each airlines bank account.
SDI recommends for Airline lookup by Airport (http://developer.flightlookup.com/). Please refer the pricing section before taking the decision
For Seat Map & Reservation SDI was able to find only this site (http://seatexpert.com/) who provides an API to display seat maps. SDI does not guarantee the accuracy of the data provided by this site.
In order for the app to function correctly for all the airlines we will need access to the airlines CRS. It seems Amadeus
SDI will provide timeline to all the features marked as TBD after receiving detaied specs from the client

## Dashboard (hidden)
Project ballpark estimate (biased to Technology)
Phase 1
This space is reserved for writing a description of the phase of work and any high level functionality and caveats.
Technology effort |  | Variables |  | ~ | Estimate Cost | INR | % | ~ % | Δ | Overview | INR | %
Development | 0 | Lead %T | 20 | 20% | Technology | 0 | #DIV/0!:divZero | 46.59% | #DIV/0!:divZero | Project | 0 | #DIV/0!:divZero
Leadership | 0 | Testing %E | 30 | 25% | Testing | 0 | #DIV/0!:divZero | 7.473% | #DIV/0!:divZero | Rework | 0 | #DIV/0!:divZero
Testing | 0 | UX %E | 12.5 | 20.22% | UX | 0 | #DIV/0!:divZero | 7.036% | #DIV/0!:divZero | Contingecy | #DIV/0!:divZero | #DIV/0!:divZero
|  | Creative %E | 30 | 36.29% | Creative | 0 | #DIV/0!:divZero | 18.12% | #DIV/0!:divZero | Total | #DIV/0!:divZero
Calculated effort |  | Client oversight | Medium | High | Delivery Mg | 0 | #DIV/0!:divZero | 12.91% | #DIV/0!:divZero
Technology | 0 | Blended rate | 10000 | 8000 | Client Services | 0 | #DIV/0!:divZero | 6.06% | #DIV/0!:divZero | Range (INR)
Delivery Mg | 0 |  |  |  | Total | 0 | #DIV/0!:divZero | 98.19% |  | #VALUE!:badFormat:[>99999]##\,##\,##0;[<-99999.99]-##\,##\,##0.00;##,##0
Client Services | 0 | Team size variables |  | ~
UX | 0 | Developers | 4 | 3 | Rework Cost | INR | D | % | ~ %
Creative | 0 | UX | 1 | 3 | Technology | 0 | 0 | 20% | 25
|  | Creative | 2 | 3 | UX | 0 | 0 | 10% | 15
Actual estimated effort |  | QA | 2 | 2 | Creative | 0 | 0 | 10% | 15
Delivery Mg |  |  |  |  | Total | 0
Client Services |  | Duration | Man | Elapsed
UX |  | Technology | 0 | 0 | Combined Cost | INR | % | ~ % | Δ
Creative |  | UX | 0 | 0 | Technology | 0 | #DIV/0!:divZero | 46.59% | #DIV/0!:divZero
|  | Creative | 0 | 0 | Testing | 0 | #DIV/0!:divZero | 7.473% | #DIV/0!:divZero
|  | QA | 0 | 0 | UX | 0 | #DIV/0!:divZero | 7.036% | #DIV/0!:divZero
|  | Total (Days) | 0 | 0 | Creative | 0 | #DIV/0!:divZero | 18.12% | #DIV/0!:divZero
|  | Total (Weeks) | 0 | 0 | Delivery Mg | 0 | #DIV/0!:divZero | 12.91% | #DIV/0!:divZero
|  | Total (Months) | 0 | 0 | Client Services | 0 | #DIV/0!:divZero | 6.06% | #DIV/0!:divZero
|  | Total (Years) | 0 | 0 | Total | 0 | #DIV/0!:divZero | 98.19%
|  | Span | Start | End | Contingency | INR | D | Δ % | ~ %
|  | Date | 2013-12-17 | 2013-12-17 | Technology | #DIV/0!:divZero | #DIV/0!:divZero | #DIV/0!:divZero | 110.8%
|  | ASSUMES WATERFALL RATHER THAN AGILE |  |  | Testing | #DIV/0!:divZero | #DIV/0!:divZero | #DIV/0!:divZero | 108.7%
[5 empty] | UX | #DIV/0!:divZero | #DIV/0!:divZero | #DIV/0!:divZero | 99.96%
[5 empty] | Creative | #DIV/0!:divZero | #DIV/0!:divZero | #DIV/0!:divZero | 155%
[5 empty] | Delivery Mg | #DIV/0!:divZero | #DIV/0!:divZero | #DIV/0!:divZero | 108%
[5 empty] | Client Services | #DIV/0!:divZero | #DIV/0!:divZero | #DIV/0!:divZero | 127.9%
[5 empty] | Total | #DIV/0!:divZero | #DIV/0!:divZero
Formulas:
Elapsed = [Man]+(G28*7)
Note on C9: Rob Green: Figure currently not linked to estimates as this is a new way of splitting tech effort
Note on F17: Rob Green: Maximum advised developers per workstream is 3

## Settings (hidden)
Settings
Lists and values
Client oversight
Very Low | 0.2 | Percent of week
Low | 0.4 | Percent of week
Medium | 0.6 | Percent of week
High | 0.8 | Percent of week
Very High | 1 | Percent of week
Feature complexity |  |  | #
Very Low | 8 | Hours | 0
Low | 16 | Hours | 0
Moderate | 24 | Hours | 0
High | 32 | Hours | 0
Very High | 40 | Hours | 0
Risk
N/A
None
Low
Medium
High

## Baseline Data (hidden)
|  |  | BARRATT INITIAL WEB BUILD | ASDA MONEY | BRANDON GENERATOR | SAUDI ARAMCO | COKE MOMENT 3 | FORMULA 1 - GP2 | AMERICAS CUP |  |  | AVERAGE
Strategy & Planning | Estimated | H | 0 | 76 | 44 | 296 | 13
|  | % | 0% | 1.976% | [7 empty] | 0.988%
| Actual | H | 26.5 | 105 | 105 | 1257.5 | 26.75 |  |  |  |  | 1520.75
|  | % | 0.4574% | 2.265% | 1.042% | 18.23% | 0.3301% |  |  |  |  | 4.008%
| Result | H | 26.5 | 29 | 61 | 961.5 | 13.75 | 0
|  | % | ! | 138.2% | 238.6% | 424.8% | 205.8% | ! | ! | ! | ! | 251.8%
| % of Tech Effort | % | 0.9456% | 4.771% | 2.116% | 43.6% | 0.7778% | ! | ! | ! | ! | 10.44%
User Experience | Estimated | H | 1015 | 428 | 0 | 0 | 377
|  | % | 18.19% | 11.13% | 0% | 0% | [5 empty] | 7.328%
| Actual | H | 983.1 | 429 | 0 | 733.25 | 387.5 | 136.5 |  |  |  | 2669.35
|  | % | 16.97% | 9.254% | 0% | 10.63% | 4.781% | 5.627% |  |  |  | 7.036%
| Result | H | -31.9 | 1 | 0 | 733.25 | 10.5 | 136.5
|  | % | 96.86% | 100.2% | ! | ! | 102.8% | ! | ! | ! | ! | 99.96%
| % of Tech Effort | % | 35.08% | 19.49% | ! | 25.42% | 11.27% | 9.854% | ! | ! | ! | 20.22%
Creative | Estimated | H | 1164 | 521 | 2112 | 523 | 765
|  | % | 20.85% | 13.55% | [7 empty] | 17.2%
| Actual | H | 846 | 582 | 2133.5 | 1580.75 | 1433 | 299.5 |  |  |  | 6874.75
|  | % | 14.6% | 12.55% | 21.16% | 22.92% | 17.68% | 12.35% |  |  |  | 18.12%
| Result | H | -318 | 61 | 21.5 | 1057.75 | 668 | 299.5
|  | % | 72.68% | 111.7% | 101% | 302.2% | 187.3% | ! | ! | ! | ! | 155%
| % of Tech Effort | % | 30.19% | 26.44% | 42.99% | 54.81% | 41.67% | 21.62% | ! | ! | ! | 36.29%
Technology (Application) | Estimated | H | 958.5 | 1504 | 1021 | 709 | 2137 | 1016
|  | % | 17.17% | 39.11% | 17.27% | 25.66% | 41.11% | 100% |  |  |  | 40.05%
| Actual | H | 1222.45 | 1351.5 | 1326 | 1332.5 | 2428.2 | 1014.75 |  |  |  | 8675.4
|  | % | 21.1% | 29.15% | 13.15% | 19.32% | 29.96% | 41.83% |  |  |  | 22.87%
| Result | H | 263.95 | -152.5 | 305 | 623.5 | 291.2 | -1.25
|  | % | 127.5% | 89.86% | 129.9% | 187.9% | 113.6% | 99.88% | ! | ! | ! | 124.8%
Technology (User Interface) | Estimated | H | 1328 | 982 | 3764 | 0 | 996 | 462
|  | % | 23.79% | 25.53% | 63.66% | 0% | 19.16% | 45.47% |  |  |  | 29.6%
| Actual | H | 1580.1 | 849.5 | 3637.25 | 1551.5 | 1011 | 370.5 |  |  |  | 8999.85
|  | % | 27.27% | 18.32% | 36.08% | 22.49% | 12.47% | 15.27% |  |  |  | 23.72%
| Result | H | 252.1 | -132.5 | -126.75 | 1551.5 | 15 | -91.5
|  | % | 119% | 86.51% | 96.63% | ! | 101.5% | 80.19% | ! | ! | ! | 96.76%
Client Services | Estimated | H | 154 | 142 | 368 | 25 | 559
|  | % | 2.759% | 3.692% | 6.224% | [6 empty] | 4.225%
| Actual | H | 246 | 123 | 406 | 598.5 | 866 | 59.5 |  |  |  | 2299
|  | % | 4.246% | 2.653% | 4.027% | 8.676% | 10.69% | 2.453% |  |  |  | 6.06%
| Result | H | 92 | -19 | 38 | 573.5 | 307 | 59.5
|  | % | 159.7% | 86.62% | 110.3% |  | 154.9% | ! | ! | ! | ! | 127.9%
| % of Tech Effort | % | 8.778% | 5.588% | 8.18% | 20.75% | 25.18% | 4.295% | ! | ! | ! | 12.13%
Delivery Management | Estimated | H | 402 | 671 | 1252 | 1186 | 726
|  | % | 7.202% | 17.45% | [7 empty] | 12.32%
| Actual | H | 485.85 | 556.75 | 1242.5 | 1279.5 | 938.5 | 396 |  |  |  | 4899.1
|  | % | 8.385% | 12.01% | 12.33% | 18.55% | 11.58% | 16.32% |  |  |  | 12.91%
| Result | H | 83.85 | -114.25 | -9.5 | 93.5 | 212.5 | 396
|  | % | 120.9% | 82.97% | 99.24% | 107.9% | 129.3% | ! | ! | ! | ! | 108%
| % of Tech Effort | % | 17.34% | 25.3% | 25.03% | 44.37% | 27.29% | 28.59% | ! | ! | ! | 27.98%
Testing | Estimated | H | 536 | 496 | 1116 | 8 | 428
|  | % | 9.603% | 12.9% | [7 empty] | 11.25%
| Actual | H | 583 | 496 | 1100 | 101 | 545 | 10.25 |  |  |  | 2835.25
|  | % | 10.06% | 10.7% | 10.91% | 1.464% | 6.725% | 0.4225% |  |  |  | 7.473%
| Result | H | 47 | 0 | -16 | 93 | 117 | 10.25
|  | % | 108.8% | 100% | 98.57% |  | 127.3% | ! | ! | ! | ! | 108.7%
| % of Tech Effort | % | 20.8% | 22.54% | 22.16% | 3.502% | 15.85% | 0.7399% | ! | ! | ! | 14.26%
Managed Services | Estimated | H | 24 | 0 | 0 | 0 | 0
|  | % | 0.43% | [8 empty] | 0.43%
| Actual | H | 73.1 | 0 | 0 | 10 | 46.75 | 47.5 |  |  |  | 177.35
|  | % | 1.262% |  |  | 0.145% | 0.5768% | 1.958% |  |  |  | 0.4675%
| Result | H | 49.1 | 0 | 0 | 10 | 46.75 | 47.5
|  | % | 304.6% | ! | ! | ! | ! | ! | ! | ! | ! | 304.6%
| % of Tech Effort | % | 2.608% | ! | ! | 0.3467% | 1.359% | 3.429% | ! | ! | ! | 1.936%
Analytics | Estimated | H | 0 | 8 | 0 | 16 | 193
|  | % | [9 empty] | #DIV/0!:noData
| Actual | H | 0 | 10.65 | 4 | 5 | 436.75 |  |  |  |  | 456.4
|  | % |  | 0.2297% | 0.03968% | 0.07248% | 5.389% |  |  |  |  | 1.203%
| Result | H | 0 | 2.65 | 4 | -11 | 243.75
|  | % | ! | 133.1% | ! | 31.25% | 226.3% | ! | ! | ! | ! | 130.2%
| % of Tech Effort | % | ! | 0.4839% | 0.08059% | 0.1734% | 12.7% | ! | ! | ! | ! | 3.359%
Total | Estimated | H | 5581.5 | 3846 | 5913 | 2763 | 5198 | 1016 |  |  |  | 24317.5
| Actual | H | 5794 | 4635.9 | 10081 | 6898 | 8104.45 | 2426 |  |  |  | 37939.35
| Result | % | 103.8% | 120.5% | 170.5% | 249.7% | 155.9% | 238.8% |  |  |  | 156%